# Programming Task Overview:  July 97

## Total Working Days: 22

Task	Programmer	Status	Duration

Game Engine Launch Sequence	ADIAZ	In Progress	3 days

Game Engine Landing Sequence	ADIAZ	Not Started	3 days

Game Engine SAR Pickup	ADIAZ	Not Started	3 days

Game Engine Pilot Eject	ADIAZ	Not Started	3 days

Navigational Map	ASOMMERS	In Progress	3 days

Load/Save Game	ASOMMERS	Not Started	2 days

Mission to Mission Object List	ASOMMERS	Not Started	3 days

Fields (Asteroids)	ASOMMERS	In Progress	3 days

Briefings Match with Movies	ASOMMERS	In Progress	2 days

Final Debriefings	ASOMMERS	In Progress	2 days

Interactive Music Integration	ASOMMERS	Not Started	2 days

FLO Scripted Cameras	ASOMMERS	Not Started	2 days

Mission System / Editor Maintenance	ASOMMERS	Ongoing	3 days

Install Program	CKARPIAK	Not Started	10 days

Implement Game 3D Sound Effects	CKARPIAK	Not Started	3 days

Explosions 2D and 3D	HDAVID	In Progress	3 days

Shield Effects	HDAVID	In Progress	1 day

Multi-Player Screens (final pass)	HDAVID	Not Started	2 days

Game Options Screen (final pass)	HDAVID	Not Started	2 days

Lights (bolts, explosions, engines)	HDAVID	Not Started	3 days

Dynamic Screens (always moving)	HDAVID	Not Started	2 days

Dynamic Main Menu	HDAVID	In Progress	2 days

Armor Hit Effect	HDAVID	Not Started	2 days

Fire From Damaged Ships	HDAVID	Not Started	3 days

Stats Screen for All Missions	HDAVID	Not Started	1 day

Postage Stamps How To for DDOWNING	HDAVID	Not Started	1 day

Multiplayer Implementation	JGRILLS	In Progress

Engine Maintenance	JGRILLS	Ongoing

Comms Being Sent at Proper Times	JHUGHES	Not Started	4 days

AI Maneuvers	JHUGHES	Not Started	3 days

AI System Maintenance	JHUGHES	Not Started	4 days

AI Check Collision	JHUGHES	Not Started	1 day

AI Heuristic Avoid Collision	JHUGHES	Not Started	1 day

AI Check Enemy	JHUGHES	Not Started	1 day

AI Maneuver Selection	JHUGHES	Ongoing	5 days

AI MED Commands Implemented	JHUGHES	Not Started	3 days

Capital Ships	PSHELUS	Not Started	5 days

Missile Trails	PSHELUS	Not Started	1 day

Swarmer Missiles	PSHELUS	Not Started	2 days

Turrets	PSHELUS	Not Started	2 days

Turret Buoys	PSHELUS	Not Started	1 day

Jump Buoys	PSHELUS	Not Started	1 day

Cockpit Tweaking	PSHELUS	Not Started	4 days

Administration	PSHELUS	Ongoing	6 days

Collision Detection	TIKEDA	Not Started	6 days

Collision Resolution	TIKEDA	Not Started	3 days

Collision Scheduler	TIKEDA	Not Started	3 days

Movie Player	TIKEDA	In Progress

# Programming Task Overview:  August 97

## BETA August 28

## Total Working Days: 21

Task	Programmer	Status	Duration

Virtual Keyboard Editor	ADIAZ	Not Started	5 days

Object Viewer	ADIAZ	Not Started	3 days

Simulator	ASOMMERS	Not Started	2 days

Improve Apparent Load Times	ASOMMERS	Not Started	3 days

Debris (better art)	ASOMMERS	Not Started	1 day

Missile Camera	ASOMMERS	Not Started	1 day

Mission System / Editor Maintenance	ASOMMERS	Ongoing	5 days

CD Switching	ASOMMERS	Not Started	3 days

Miscellaneous	ASOMMERS	Ongoing	6 days

Demo	FROAN	Not Started	21 days

Hardware Effects	HDAVID	Not Started	4 days

Software Effects	HDAVID	Not Started	4 days

Lens Flares	HDAVID	Not Started	1 day

Damaged Textures	HDAVID	Not Started	3 days

Hazing / Nebula Effect	HDAVID	Not Started	2 days

Cloaking Effect	HDAVID	Not Started	2 days

Credits	HDAVID	Not Started	3 days

Auto Save and Load	HDAVID	Not Started	1 day

Exit Game Plaque	HDAVID	Not Started	1 day

Multiplayer Implementation	JGRILLS	In Progress

Engine Maintenance	JGRILLS	Ongoing

AI Maneuvers	JHUGHES	Not Started	10 days

AI System Maintenance	JHUGHES	Not Started	5 days

AI When To Attack Cap Ships	JHUGHES	Not Started	1 day

AI Attack Cap Ship Components	JHUGHES	Not Started	5 days

Cloaking Device	PSHELUS	Not Started	1 day

Ship/Object Damage and Repair	PSHELUS	Not Started	3 days

Powerups	PSHELUS	Not Started	3 days

Articulated Fighter / Bomber Parts	PSHELUS	Not Started	2 days

Wasp Tail	PSHELUS	In Progress	1 day

Cockpit Beams	PSHELUS	Not Started	1 day

Camera tweaking	PSHELUS	Not Started	2 days

Administration	PSHELUS	Ongoing	8 days

Collision Scheduler	TIKEDA	Not Started

Movie Player	TIKEDA	In Progress

# Programming Task Overview:  September 97

## Total Working Days: 21

Task	Programmer	Status	Duration

Bug Fixes	ALL	Not Started	21 days

Demo	FROAN	Not Started	21 days

Administration	PSHELUS	Ongoing	8 days

# Programming Task Overview:  October 97

## FINAL October 23

## Total Working Days: 23

Task	Programmer	Status	Duration

Bug Fixes	ALL	Not Started	23 days

Administration	PSHELUS	Ongoing	8 days

# Programming Task Overview:  November 97

## SIGN OFF November 6

## Total Working Days: 4

Task	Programmer	Status	Duration

Bug Fixes	ALL	Not Started	4 days