file: $/wc5/doc/technical/hugh/march.doc

description: hugh's tasks for march '97 listed for TDD.

author: hugh david, (c) origin systems, 1997

version: draft

_____________________________________________________________________________________

task name:	particle system, explosions and debris (final pass)

time scheduled:	5 days

time spent:	0

status:		not started

technical description (description of the task and what will be involved to complete it):

expand on and complete first-pass code to provide game-quality explosions and debris.

integrate wc4 bitmap explosions.

finalize data format for designer-configurable explosions. (like bullets ?). work with MED, andy sommers & designers. explosions can be "added" to objects.

qualitative &/or quantitative descriptions for explosions, e.g: "big particle explosion", "medium particle explosion with 10% chance of bitmaps", "small particle explosion with lots of generator particles", etc.

investigate use of  particle-system-specific memory manager, overloading new & delete operators.

allow for explosions / particles to be lights.

required: design team time.

required: some of andy sommers time. (MED integration).

checklist (what we'll see and how to determine task completion ):

general explosions / particle systems and debris that can be easily configured through data files.

comments:

since i may need to synchronize this work with others, perhaps i should work on the game option screen first.

_____________________________________________________________________________________

_____________________________________________________________________________________

task name:	game options screen (first pass)

time scheduled:	5 days

time spent:	0

status:		not started

technical description (description of the task and what will be involved to complete it):

work on / with save-game data format.

display menu screen of some user-configurable options.

accept various user inputs.

display options as user navigates menu system.

work on / with menu system data & code.

work on export class for user-alterable data. should this data exist in the menu system, or should it be in a separate export class ?

more menu code to support more extensive data format support of menu-alterable options.

more data-driven support of looks of menus ("cookies" as FORMs).

i would like: input & feedback from design team.

checklist (what we'll see and how to determine task completion ):

resolution-independent game options screen on top of spaceflight.

some variables are seen to affect the game.

comments:

i'm ready for resolution-scaleable bitmaps.

_____________________________________________________________________________________

_____________________________________________________________________________________

task name:	langauge manager (final pass)

time scheduled:	5 days

time spent:	0

status:		not started

technical description (description of the task and what will be involved to complete it):

separate xmf/iff data files for each language ?

research & test double-wide character set support, e.g.: glyph mapping in 2 bytes.

split text string definition data into sensible separate files.

expand langauge interface to include language-independent pixel-specific text formatting in 1 and 2 dimensions. (screen xy).

required: do we ship with exactly 1 language per sku ?

required: what support can we expect in translation tool ? in subtitling tool ?

required: feedback on LANGUAGE.DOC from developers & translations department.

checklist (what we'll see and how to determine task completion ):

translations department can translate game by just changing a data file of a well-documented format.

translation tool to ease translators' jobs.

comments:

this task was going well. i want this final stage to go well too. please FEEDBACK ME UP !!! please read $/wc5/doc/technical/language.doc

since i would like to have input from others on the development team and also from the translations department, this task may have to wait until later in the month.

it may not be possible for me to promise that this system is final until i have all the feedback i need.

_____________________________________________________________________________________